## Deployment-Checklist
BeeOS - Production Deployment Cheklist
Updated 23.Jan.2026
Highlight Note: N/A
PROD Deployment Checklist
# | Checklist Item | More details | System (BE/FE) | Assigneee | Start Date | End Date | From Hour - To Hour | Status | Note
1 | Clone Vinova Staging to production server | clone database | Backend | Marvin + Ken (Otis) | 2026-01-26 | 2026-01-26 |  | N/A
2 | Deploy the latest code (both BE, FE) to production environment. | Note: turn ON the maintenance mode >>> To prevent new data inserting into the DB | Backend+Frontend | Ken (Otis) + Daniel | 2026-01-26 | 2026-01-26 |  | N/A
3 | Check domains configuration | domains configuraiton has been configured properly? ----------------------- CMS Portal: : app.beevn.com.vn API services: api.beevn.com.vn | DevOps | Marin | 2026-01-26 | 2026-01-26 |  | Done
4 | Check if MAINTENANCE mode is ON on the CMS |  | Frontend | Daniel | 2026-01-26 | 2026-01-26 |  | N/A
5 | Check Email server configuration. | Email server configuraiton has been configured properly? | Backend | Ken (Otis) | 2026-01-26 | 2026-01-26 |  | N/A
6 | Check Zalo configuration | Zalo OA configuraiton has been configured properly? | Backend | Ken (Otis) | 2026-01-26 | 2026-01-26 |  | N/A
7 | Check other permissions (e.g.: AWS's S3 right permissions, logging write permission) |  | DevOps | Marin | 2026-01-26 | 2026-01-26 |  | Done
8 | Roll back plan definition | Define the roll back activities here >>> Purpose: Roll it back to to the previous working version in the worst case (with Maintenance if OFF) | Backend | Ken (Otis), Marvin (Louis) | 2026-01-26 | 2026-01-26 |  | Done
9 | Turn OFF Mainteance mode | Turn off for verification | Backend | Ken (Otis) | 2026-01-26 | 2026-01-26 |  | N/A
10 | Quick test (CMS with user roles & Mobile responsive) Purpose: To make sure pointing to the correct AWS env | Quick test 1. Logging in wih user roles: Admin, Underwriter, Leader, Claim-Officer to make sure account login successfully. 2. Mobile responsive to Leader role. | QC + Vy (BeeVN) | Levi/Lani, Vy (BeeVN) | 2026-01-26 | 2026-01-26 |  | N/A
11 | System mornitoring | Keep mornitoring Purpose: to make sure not having any unusual stuffs happens. | Backend / DevOps | Ken (Otis), Marvin (Louis) | 2026-01-26 | 2026-01-26 |  | Done
12 | Inform the customer the team has finished migration |  |  | Tony | 2026-01-26 | 2026-01-26 |  | N/A

## Oher Note
BeeOS - Other Note
Updated 23.Jan.2026
# | Item | More details | Status | Other reference
1 |  |  | N/A
2 |  |  | N/A
3 |  |  | N/A
4 |  |  | N/A