# Content Strategist: 2-Month Work Scope

OS Research | February 2026

# Role Allocation

| Area | % | Focus |
| --- | --- | --- |
| Research & Analysis | 20% | VC, startup ecosystem, innovation, business models |
| Content Transformation | 20% | Research → analysis, education, case studies |
| Company Voice | 30% | LinkedIn, Meta, Google, X — consistent messaging |
| Internal Operations | 30% | Internal comms, knowledge base, UX writing |

# Month 1: Foundation & Setup

## Week 1-2: Research Foundation (20%)

• Deep dive into OS Research playbooks and methodology

• Study Vietnam VC landscape and startup ecosystem

Deliverable: Research Digest #1 + Ecosystem Map

## Week 2-3: Company Voice Setup (30%)

• Define Brand Voice Guidelines: tone, vocabulary, style

• Set up profiles: LinkedIn, Meta, X, Google Business

Deliverable: Brand Voice Guide + Platform Playbook

## Week 3-4: Internal Operations (30%)

• Create internal comms templates and knowledge base structure

• Begin UX writing audit for product interfaces

Deliverable: Knowledge Base v1 + Internal Templates

# Month 2: Execution & Production

## Week 5-6: Content Transformation (20%)

• Transform startup research into public case studies

• Draft educational article series from playbooks

Deliverable: Case Study #1 + 3-part article series draft

## Week 6-7: Company Voice Launch (30%)

• Publish first content across all platforms

• Execute distribution and community engagement

Deliverable: 8+ pieces published + engagement tracking

## Week 7-8: Internal Operations Scale (30%)

• Complete knowledge base organization

• Document content creation workflows and SOPs

Deliverable: Content SOP + Weekly internal newsletter

# Success Metrics (End of Month 2)

| Area | Target |
| --- | --- |
| Research (20%) | 2 research digests, ecosystem map created |
| Content (20%) | 1 case study published, 10+ content ideas in pipeline |
| Voice (30%) | All platforms live, 8+ posts, 100+ engagements |
| Internal (30%) | Knowledge base organized, SOPs documented |

# Key Principles

1. Research feeds everything — content traces back to real experiments

2. Internal before external — strong systems enable consistent voice

3. Quality over quantity — 1 great case study > 10 mediocre posts

4. Document as you go — every process becomes knowledge base

5. Engage, don't broadcast — conversation, not megaphone